## Slide 1: BMW Global IAM -Agentic Solution
23rd April

## Slide 2: Enabling the IAM Transformation through Agentic AI
The solution leverages Data and Agentic AI to transform IAM field operations into an intelligent, insight‑driven engagement model - enhancing dealer/IR engagement and accelerating genuine spare parts growth
The transformation is enabled through three tightly integrated components:
The overall Agentic AI systems act as digital companions and orchestration engines, capable of:
Intelligent planning of field visits
AI-assisted dealer/IR engagement
Automated reporting and knowledge capture
Field force orchestration for management
Travel optimization through route planning
This enables BMW to shift from manual field execution to intelligent, agent‑driven IAM orchestration.
1. Agentic Sales Companion
Enhancing the effectiveness of individual field representatives
2. Field Force Orchestration
Providing management oversight, coordination, and control
3. Intelligent Route Planning
Minimizing travel time while maximizing visit coverage

## Slide 3: Modules included in Agentic Sales Companion
Intelligent
Planner
Activity planner to prioritizes dealer and IR visits based on performance insights, past interactions, and recommended actions for the day or week
Structured Visit
Capture & Reporting
Structured report template to capture the visit discussions and a tool to automatically converts inputs into clean, NSC-ready reports and follow-up summaries
Dynamic Knowledge
Assistant
A knowledge assistant to provides instant answers on products, policies, tools, and processes using a RAG-based knowledge repository
Supporting Operational Activities
Tool to automate the routine operational activities - follow-up emails, sharing materials, providing technical assistance, and nudging for timely responses

## Slide 4: The Agentic Solution Delivers IAM Value Across Key Dimensions
The agentic solution translates core capabilities into measurable gains across efficiency, field productivity, dealer engagement, and management visibility- directly supporting aftermarket growth.
Solution Component | Key Solution Capability | Efficiency Gains | Higher Productivity & Sales | Better Dealer / IR Engagement | Improved Management Visibility
1. Agentic Sales Companion | Intelligent planning of field visits | Reduces manual time spent reviewing dealer data AI prioritizes high-potential garages | Focus on high-opportunity dealers/IR Improves visit effectiveness and conversion | Ensures regular engagement with key IAM dealers/IR | Enables analysis of visit coverage and planning effectiveness
 | AI-assisted dealer / IR engagement | Reduces preparation time for sales discussions AI generates contextual talking points | Improves conversion of visits into genuine parts orders Enhances effectiveness of each visit | Tailored conversations aligned to dealer/IR needs Builds stronger dealer relationships | Captures dealer feedback and interaction insights
 | Automated reporting and knowledge capture | Eliminates manual report preparation Reduces reporting time significantly | Frees time for additional field visits Improves sales rep productivity | Ensures structured documentation of dealer interactions | Real-time field insights captured for central analysis
2. Field Force Orchestration | Field force orchestration for management | Reduces manual coordination of field activities | Enables optimized allocation of reps | Ensures balanced dealer engagement across territories | Real-time dashboards on field performance, coverage, and activity.
3. Route Optimization | Travel optimization through route planning | Reduces travel time between visits | Enables more dealer visits per day | Increases frequency of dealer engagement | Provides insights into territory coverage and travel efficiency
The expected efficiency gain (reduced work effort) approximately ~ 40%. A detailed analysis of work packages 13-18 can be found here
Key Dimensions

## Slide 5: Costing
Agentic Sales Companion
(6 Months)
Field Force Orchestration
(3 Months)
Intelligent Route Planning
(1.5 - 2 Months)
$ 400 K
~1400 Man days at an Average blended daily cost rate of $300
$ 150 K
~500 Man days at an Average daily rate of $300
$ 100 K
~300 Man days at an Average daily rate of $300
Additional Cluster Rollout
(2-3 Months)
$ 60 K **
Typically, 1 cluster covers 3-4 markets *. But we can add more markets within a cluster with minimal incremental cost, providing flexibility in rollout design
Number of markets in a cluster depends on multiple factors including - size of the market, data system landscape, regulatory requirements, language, DMS system, NSC structure Geographic proximity etc.
Platform cost is not included in the above costing. It will be around 5K per month and may vary depending on storage, compute, foundational model usage, API request, concurrent users, market deployed etc.
Maintenance and operations will be managed by the team during the build and rollout phase. After that period (approx. 2/3 years once all markets are deployed), there will be a monthly cost of $5K-$7K
The solution is designed as a single unified platform across all markets. Where local legal, data sovereignty, or compliance requirements mandate for a market a separate localized build, additional setup effort and investment will apply
** Additional cost will be added if there is a significant deviation on the data, cloud platforms, DMS system etc.
Any capability additions beyond the agreed in-scope modules including AI pitch generation, training enablement, IR onboarding, continuous improvement or advanced analytics will be scoped, estimated, and priced separately as Phase 2 enhancements and are not reflected in the current cost model
Penetration testing, security audits, and compliance assessments required by BMW IT or local regulators before launch are not part of the build cost and will be separately scoped and priced according to market needs and audit scope.
The tool will be configured to NSC-defined KPIs, targets, and report formats confirmed at the start of deployment. Changes to KPI definitions, target thresholds, or report structures after build require reconfiguration at additional cost
First Time build – one market/one cluster
Notes: Build ($830k) and run ($225k) components

## Slide 6: Resource Plan
Roles | Level | Agentic Sales Companion (FTE) | Field Force Orchestration (FTE) | Intelligent Route Planning (FTE) | Market Rollout (FTE)
D&A QA Lead/SMA | Level 5 | 0.5 | 0.5 | 0.25 | 0.2
Delivery Lead | Level 6 | 1 | 1 | 1 | 1
Gen AI Architect | Level 6 or Level 7 | 0.5 | - | 0.1 | 0.1
Gen AI Developer / Scientist | Level 8 or Level 9 | 3 | 2-3 | 2-3 | 1
Prompt Engineer | Level 9 | 0.5 | - | 0.5 | -
IAM Business Consultant | Level 9 or Level 11 | 0.5 | 0.5 | - | -
Full Stack Developer | Level 8 or Level 9 | 1 | - | 0.5 | 0.5
Dev Ops Engineer | Level 8 or Level 9 | 2 | 1 | 1 | 0.5-1
Data Engineer | Level 9 | 1 | 0.5-1 | 1 | 0.5-1
ML Engineer | Level 9 | 1 | 0.5-1 | 1 | 0.5-1
Knowledge Graph / Embedding / Storage Developer | Level 9 | 1 | - | - | 0.25
Tester | Level 10 or Level 11 | 0.5 | 0.25 | 0.25 | 0.25
UX Developer | Level 9 | 2-3 | 1-2 | 1 | 0.5
RAI Consultant | Level 9 | 0.25 | - | 0.25 | 0.25
1400 Man-Days
500 Man-Days
300 Man-Days
200 Man-Days
LCR
125
65
50
35
35
30
25
25
25
25
30
20
25
30

## Slide 7: Assumptions (1/2)
The AI solution eliminates ~2-3 hours of daily admin per rep, freeing time for more selling, and progressively enabling workforce optimization
30% - 40%
Reduction in admin effort per sales rep starting from Month 6
+2 - 5
Additional dealer/IR visits per rep per week
13-16 FTE
Reduction due to AI intervention, in addition to the ongoing decrease in FTEs resulting from the learning curve
OR
~
Assumptions underlying the 30-40% efficiency gain:
Tool adoption: Rep adoption must be consistent on a daily basis. Any reduction in tool adoption will directly impact efficiency gains and undermine the FTE reduction targets
Adherence to recommendations: Reps must act on the tool's visit priorities, suggested agendas, and action recommendations - not override them habitually.
Territory stability: Rep territories must remain broadly stable during the measurement period. Frequent territory realignments reset the tool's learning, distort efficiency baselines, and make performance attribution unreliable
Technical Readiness: Efficiency gains are realized under the assumption that there are no technical challenges including network connectivity issues or device limitations in the field during rep interactions
Data Availability: We assume all data required for analysis, COE reports, and master data is available, accessible, and in the desired format. Any delays, incompleteness, or inconsistency in data availability will reduce AI output quality and directly impact overall efficiency delivery.
Conversion of the efficiency into FTE reduction is an operational activity and should follow a formal decision gate for redeployment: FTE reduction decisions must pass through a structured, jointly governed redeployment gate, not be taken ad hoc. The gate must assess the following factors before any redeployment is approved (else the translation will not happen as desired FTE reduction):
  Language capability: A rep redeployed into a new territory must be able to operate effectively in the local language. Mismatched language capability increases effort and undermines relationship quality, offsetting the efficiency gain.
  Geographical feasibility: Travel distances, cross-border logistics, and physical accessibility of the territory must be viable for the redeployed rep. An efficient route plan cannot compensate for an unworkable geography
  Change in market structure or commercial model: Significant changes to the IAM commercial model such as the introduction of new distribution tiers, changes to dealer agreements, or shifts in NSC governance during the deployment period may invalidate efficiency baselines and require recalibration of the tool's prioritization logic
  Minimum viable rep density per territory: Each territory must maintain a minimum rep coverage threshold - below which service quality, visit frequency, and dealer relationships deteriorate.

## Slide 8: Assumptions (2/2)
API Access To System: We assume API access is available for all in-scope source systems with a clear API documentation and authentication methods for each
Historical data availability: A minimum of 12 months of clean, structured historical visit, sales performance, and dealer KPI data is assumed to be available across all in-scope markets before the Data Foundation phase begins.
Connector availability for existing systems: Standard API connectors are assumed to be available for all in-scope source systems - including Salesforce, SAP S/4HANA, and the primary DMS vendor per market.
Master data consistency: Dealer and IR master data - including contact details, territory assignments, tier classifications, and ordering platform registration status - is assumed to be complete, current, and consistently maintained across source systems.
Data residency compliance: Data residency and sovereignty requirements per market are assumed to be addressable within the AWS multi-region architecture.
NSC report format stability: The NSC report format confirmed at the start of deployment is assumed to remain stable throughout the build and rollout period.
NSC report in digital format: Existing NSC reports are assumed to be available in a structured digital format - not handwritten, scanned, or unstructured PDF - that can be parsed programmatically.
NSC portal programmatic access: Programmatic access to the NSC Portal or SharePoint to retrieve and submit reports is assumed to be technically feasible and approved by BMW IT within the Design & Discovery phase.
Workforce planning commitment: The translation of efficiency gains into FTE reduction requires active workforce planning decisions. These decisions sit entirely outside Data & AI scope of delivery. Data & AI delivers the efficiency; market/sales team realizes the FTE saving.
Translation Accuracy - The inbuilt translation models available in could will be used for all the translation layer and the accuracy of the same is assumed to be sufficient for the reports
Foundational Model Usage - A hybrid approach will be used when selecting the foundational model, considering the complexity of the work (for example, Claude Sonnet for complex generation and Claude Haiku for summarization and retrieval)

## Slide 9: Workplan For Build Phase
Tasks | Details
Design & Discovery | Capture NSC process, KPI definitions, data source mapping, system access, language & regulatory assessment, Front end design, Market Cluster Identification, Knowledge base content, Formal D&D sign-off
Infrastructure & Environment Setup | Setup of database schemas, storage buckets, vector store namespaces, API gateway, and networking configuration etc.
Data Connectors Build | Data connection pipeline build to enable a continuous data receipt, new connector development for different DMS / CRM / ERP
Data validation and quality checks | Profiling, gap identification, cleansing, and baseline establishment before agent build begins
NSC template configuration | Build market KPI targets, dealer/IR tier structure, visit frequency targets, NSC report template etc.
CI/CD Pipeline Build | Set up source code repository, automated build and test pipelines, staging and production deployment
Agent build - Agentic Sales Companion | Build and unit test all agents - Orchestrator, Intelligent Planner, Visit Capture, Knowledge Assistant, NSC Report Generator, and Operational Activities
Agent build - Intelligent Route Planning | Integrate tools enabling routing engine and build daily route generation agent
Prompt Engineering & Tuning | Prompt calibration and fine tuning for the all agents
MCP (Model Context Protocol) build | Build tool connection layer linking agents to data sources and APIs via MCP
RAG knowledge base ingestion | Market-specific documents ingested, chunked, embedded, and validated for retrieval accuracy
Language and localization validation | Configure Translate module for dynamic AI content, add market-specific tone instructions to prompts
Front end build | Build ReactJS frontend with necessary capabilities as agreed in the design & discovery phase
Integration testing | Validate end-to-end data flow from source system to agent output to NSC report submission
Tenant provisioning Build | Build Terraform to provision fully isolated market environment - database, storage, vector store, API gateway
Migration to Production | Validate production environment, replicate staging configurations, rotate production credentials, migrate and validate historical data, execute deployment with zero downtime
UAT with local rep cohort | Structured testing covering semantic accuracy, report quality, tool robustness, and field usability under real visit conditions
Go live and NSC sign-off | Formal acceptance of report format and KPI accuracy by NSC management before go-live

## Slide 10: Workplan For Rollout Phase
Tasks | Details
Design & Discovery | Capture NSC process, KPI definitions, data source mapping, system access, language & regulatory assessment, Front end design, Market Cluster Identification, Knowledge base content, Formal D&D sign-off
Tenant Provisioning | Execute automated Terraform run to provision fully isolated market environment - DB schema, S3 prefix, vector namespace, API gateway etc.
Data Connectors Config/Build | Same-stack: reuse existing connectors, point to new market credentials and endpoints. Different-stack: build new connector for unfamiliar DMS or CRM
Data validation and quality checks | Profiling, gap identification, cleansing, and baseline establishment before agent build begins
RAG knowledge base ingestion | Market-specific documents ingested, chunked, embedded, and validated for retrieval accuracy
Language and localization validation | Configure Translate module for dynamic AI content, add market-specific tone instructions to prompts
MCP (Model Context Protocol) Reconfigure | Reconfigure tool connection layer linking agents to data sources and APIs via MCP
Integration testing | Validate end-to-end data flow from source system to agent output to NSC report submission
Prompt Engineering & Tuning | Prompt calibration and fine tuning for the all agents
Front end Reconfigure | Reuse ReactJS frontend with necessary capabilities as agreed in the design & discovery phase
Migration to Production | Validate production environment, replicate staging configurations, rotate production credentials, migrate and validate historical data, execute deployment with zero downtime
UAT with local rep cohort | Structured testing covering semantic accuracy, report quality, tool robustness, and field usability under real visit conditions
Go live and NSC sign-off | Formal acceptance of report format and KPI accuracy by NSC management before go-live

## Slide 11: Workplan For Operations/Maintenance Phase
Tasks | Details
Platform Monitoring | Review alert dashboard - log anomalies, performance degradation, API errors, pipeline sync failures etc.
Bug Fixes & Incident Resolution | Fix reported bugs covering agent errors, data pipeline failures, frontend issues, connector breaks, integration failures etc.
Security Patching & Infrastructure Updates | Apply security patches and dependency version updates on a regular basis
Governance & Monthly Reporting | Prepare monthly BAU review pack - platform health, adoption metrics, open issues, and present to BMW in monthly governance review

## Slide 12: Key Risks And Mitigations
Category | Risk | Details | Mitigation
Data & Integration Risks | Data access delays | BMW IT security approvals and API access grants take longer than anticipated - blocking connector build and delaying future process | Initiate IT security review in Week 1 of D&D Build connector stubs using synthetic data during access approval period to maintain build momentum. Escalate via Delivery Lead if API access not confirmed by end of W4.
Data & Integration Risks | Poor data quality | Source system data is incomplete, inconsistently structured | Mandatory data quality assessment in D&D - minimum viable data confirmed per market before build begins.
Data & Integration Risks | Source system schema changes | BMW makes changes to source system APIs, data structures, or field mappings post-connector build breaking live data pipelines without warning and causing silent data degradation | BMW IT commits to notifying the operations team minimum 2 weeks before any planned source system change.
Data & Integration Risks | NSC report inconsistency across markets | Existing NSC reports vary significantly in structure between markets forcing market-specific extraction layers rather than a single shared pipeline | Confirm NSC report structure for all in-scope markets in D&D before build begins. Sample reports collected and reviewed in weeks 1/2
AI & Technology Risks | AI output quality degradation | Agent output quality degrades over time as LLM providers update models, data patterns shift, or the knowledge base becomes outdated | RAG knowledge base refreshed quarterly - BMW provides updated documents. Model version transitions always tested in staging before production switch. Never switch LLM versions cold in production.
AI & Technology Risks | Orchestration latency at scale | Multi-agent orchestration response times exceed the threshold time under concurrent user load - degrading the field rep experience and accelerating tool abandonment | Load testing at expected peak concurrency completed before UAT, not after Prompt caching for repeated dealer context and model routing (Haiku for summarization, Sonnet for generation) implemented from build to control latency and cost simultaneously
AI & Technology Risks | LLM cost overrun | Unmonitored LLM API usage across markets at full scale drives platform costs significantly above the estimate | Monthly cost governance review by Data Scientist - usage per market, per workflow, per model tracked and reported to BMW.
Delivery & Program Risks | Low rep adoption | Field reps revert to manual habits within weeks of go-live - using the tool inconsistently or partially - reducing efficiency gains below projected levels and making FTE reduction targets indefensible. | NSC management enforcement mandated as a program governance condition - not optional Adoption tracked from Day 1 - usage rate, report submission rate, visit capture completion monitored daily during hypercare. Below 60% triggers immediate intervention.
Delivery & Program Risks | Scope creep post D&D sign-off | BMW requests capability additions or workflow changes after D&D sign-off - expanding scope mid-build, compressing delivery timeline, and creating cost overrun without a corresponding budget adjustment | Formal change control process established at D&D sign-off. All post-sign-off changes require a written change request with effort and cost impact assessment before execution begins.
Delivery & Program Risks | BMW stakeholder unavailability | NSC product owners or data contacts are not available during Discovery windows, UAT periods, or sign-off gates - stalling config specification, delaying UAT execution, and pushing go-live dates for entire clusters. | BMW commits named NSC product owner and data contact for each market as a signed program governance condition before cluster schedule is agreed.
Compliance & Regulatory Risks | GDPR data residency violations | Market data routed to incorrect cloud region - for example, German dealer data processed outside the EU - constituting a GDPR violation | Data residency requirements confirmed per market in D&D. Region assignment hardcoded in Terraform per market tenant - not configurable at runtime.
Compliance & Regulatory Risks | Regulatory market complexity - China | China's data sovereignty laws, platform restrictions on foreign LLM providers, and local regulatory approvals require a fully localized build that is significantly more complex and expensive than standard cluster replication. | Local regulatory and legal review initiated in parallel with Phase 1 to understand full compliance requirements and timeline before China build is scoped.
Compliance & Regulatory Risks | BMW IT security approval delays | BMW IT security review for cloud deployment, LLM API calls, and SSO integration takes longer than the budgeted timeline in the program plan | Security review initiated in Week 1 of D&D - not after D&D sign-off BMW IT security owner named at program kick-off with fortnightly checkpoint meetings. Delays escalated to program sponsor immediately

## Slide 13: Dependencies to have Field Force Orchestration ready on day 1
Field Force Orchestration can be built and ready from Day 1 and we can start building it before the main program formally kicks off.
The approach is straightforward: Field Force Orchestration will read existing NSC reports already sitting in the NSC Portal / SharePoint which is been updated manually by the field rep, post-process them, and generate the KPIs, tables, and views for the management frontend.
However, to make this work cleanly, we need the following confirmed by the team before build begins:
  NSC report consistency - are the existing NSC reports broadly consistent in structure and format across all markets? If structure varies significantly, the extraction layer needs to be built market-by-market
  NSC System - What NSC system or platform is currently used to generate, store, and manage NSC reports - is it SharePoint, a proprietary portal, or a third-party system?
  Sample NSC reports - full samples for all in-scope markets, with all fields, tables, KPIs, and formatting detail, as aligned with the BMW team
  Field Force Orchestration frontend requirements - a clear list of all elements, KPIs, views, and tables to be displayed in the Field Force Orchestration frontend, along with the source field in the NSC report for each
  Language confirmation - are existing NSC reports written in English or in local market language? This determines whether a translation layer is needed before parsing, which has architectural and accuracy implications
  Access to the NSC Portal / SharePoint - confirmed API or file access to retrieve reports programmatically, including any IT security approvals required
Once the Agentic Sales Companion goes live and starts generating structured visit data, Field Force Orchestration will switch its data source from existing NSC reports to Sales Companion output.

## Slide 14: Additional Questions We Need to Clarify with the Team
What BMW interfaces and systems are currently used across all markets including CRM, DMS, ERP, NSC portal, and any market-specific systems etc.
Are there any systems currently behind VPN, firewall, or private network that would require additional BMW IT infrastructure work to expose for integration?
Are existing NSC reports broadly consistent in structure and format across all markets? If structure varies significantly between markets, the Field Force Orchestration extraction layer needs to be built market-by-market - significantly increasing build effort and cost
Are there known data quality issues, gaps, or inconsistencies in any market's source systems that the team should be aware of before data validation begins?
What visit frequency targets are set per dealer tier and IR tier in each market?
What is the current visit report format and submission process in each market - paper, email, digital form, or CRM entry? This determines the baseline against which the automated report generator is designed
Is there a master data management process currently in place for dealer and IR data?

## Slide 15: AI empowers field teams to move from Administration Tasks to Selling better- Cutting efforts across Dealer and IR journeys
Non-Exhaustive
Illustrative
Dealer Visit
Dealer Assessment
Dealer Coaching
Customer Visit
Customer Assessment
Pre-Visit
On-site
Post Visit
KPI & performance one‑pager generation, supporting field team conversations
Up to
~34%
Standardized Assessment preparation, with highlighted KPIs and focus areas, enabling field teams with a clear diagnostic lens
Up to
~68%
Effort reduced by
~34%
Effort reduced by
~34%
Route planning and pitch preparation, helping with customer qualification and funnel management
Real‑time meeting co‑pilot capturing discussions, key issues, and generating action plans and formalizing interactions
Up to
~33%
Capture assessment discussions; auto‑generate structured summaries for sign‑off, helping field teams to run evidence‑based assessments
Up to
~42%
Effort reduced by
~34%
Up to
~21%
Drafts visit reports & follow‑up communications, helping reduce post‑visit administrative fatigue
Up to
~68%
Effort reduced by
~34%
Effort reduced by
~34%
Tailored coaching content and agenda generation, empowering field teams and increasing trainer productivity
Up to
~34%
Optimized route planning and tailored sales pitches, enabling field teams to cover more outlets while delivering relevant, personalized first impressions.
Up to
~40%
Up to
~40%
Record and summarize coaching conversations, support Dealer development & enhance training scores
Up to
~19%
Provide guided onboarding support & draft next steps in real time, helping field teams answer questions and drive faster conversions
Customize assessment questionnaires and drafts next steps, to identify gaps faster and deliver consistent, high‑quality recommendations.
Up to
~21%
Automate assessment reporting, enabling field teams to quickly move from documentation to next actions without manual reporting overhead
Up to
50%
Draft coaching summaries and set up follow‑up customized trainings, reinforcing learning outcomes and helping field teams ensure continuity
Up to
~34%
Auto‑generates post‑visit actions and emails, supporting field teams with timely follow‑ups and reducing missed commitments.
Up to
~50%
Automates assessment summaries and follow‑ups, to minimize post‑visit administrative load and improve productivity
Up to
~60%
Potential AI interventions & Benefits
Indicative reduction in Efforts (in %age)